## Shipping Scorecard
Delivering the right products, the right time to the right place, at the right cost | 0 | 1 | 2
Measure of Success Description | Below | Expected | Exceed | Weighting | Actual Measurement | Frequency | Responsible Role
Paid Driver hours / mile | 0.0542 |  | 0.0513 | 25% | Total Driver Labor Hours / Total Actual Miles | Weekly | Manager
Shipping Miss % | 0.31% |  | 0.16% | 50% | Shipping wrong place, missed delivery time, damaged product during unloading / Total Stops | Weekly | Manager
Actual vs Expected Miles | 1.09 |  | 1.05 | 25% | Actual miles used / Expected calculated miles | Weekly | Dispatch
Note on D3: Mitch Millstein: Have to factor in 2 guys that shuttle (adding only 50 miles each to total mileage) but adding full paid hours Otherwise we would use 500 miles as the standard
Note on D5: Mitch Millstein: 5% is for road-closed/re-route factor/bad directions 12% is for after the route is calculated we add on average 50 more miles for the driver to drive (based on a 425 expected)
Note on F2: Mitch Millstein: Where is the data tracked. Note: can be same as measure of success
Note on G2: Mitch Millstein: weekly monthly quarterly and YTD or Rolling 12 mo
Note on H2: Mitch Millstein: Title of the person who is reponsible for tracking the measure and acting on it

## Action Plan
# | Issue | Role | Idea/Solution | Benefit (High/Low) | Imp. (Easy/Difficult) | Owner | Start Date | Target Date | Closed | STATUS
3 | Sales Rep fills out change order form (filling in all header info) | Sales Reps | Sales Rep changes the order in the system (no paper) | Medium | Medium | Tim | 2007-06-19 | 2007-08-01 |  | Training Sales Reps
4 | Sales Admin Fills out Change-Order Form on-line from paper form (filled out by Sales Rep) | Sales Admin | Sales Rep change the order in the system | Medium | Medium | See #3 | 2007-06-19 | 2007-08-01
5 | Emailing change-order notification | Sales Admin | Stop Doing | Low | Easy | Ed/Tim | 2007-06-19 | 2007-07-13
7 | Sales Admin checks for missing delivery info (on order, check folders, call customer) | Sales Admin | Enter order, and Sales Rep gets delivery info every time Sales Rep asks for and calls the contractor Field in system for Contractor Phone # Policy for leaving delivery info on our vmail (job #, extension) | High | Medium | Tim / Ed | 2007-06-19 | 2007-07-20
8 | Kelly and Helen meet to review mising delivery info | Sales Admin | No need for meeting if Helen is not checking for missing delivery info by calling customers | High | Medium | See # 7 | 2007-06-19 | 2007-07-20
8 | Kelly and Helen meet to review mising delivery info | Shipping Admin | No need for meeting if Helen is not checking for missing delivery info by calling customers | High | Medium | See # 7 | 2007-06-19 | 2007-07-20
9 | Helen finds out that customer needs to cancel/delay/expedite order | Sales Admin | No need to do this if Helen is not checking for missing delivery info | High | Medium | See # 7 | 2007-06-19 | 2007-07-20
10 | Kelly checks orders for missing delivery info | Shipping Admin | No need to do this, all orders will have delivery info by this step | High | Medium | See # 7 | 2007-06-19 | 2007-07-20
10.5 | Kelly calls for date confirmation | Shipping Admin | Stop Doing | Medium | Easy | Frank / Kathy / Tim | 2007-06-19 | 2007-07-20
11 | Kelly creates change order form to change delivery date and sends it to Sales Admin to enter | Shipping Admin | Shipping admin changes the order in the system System must email sales rep all changes to their orders | Medium | Medium | Cathy | 2007-06-19 | 2007-07-01
12 | Print 2 copies of worksheets (1 to keep in order and 1 to sort by state) so Rod can bring a packe thome | Dispatch | Create a report in job # sequence to reference with worksheet details | Medium | Easy | Ed | 2007-06-19 | 2007-07-13
12a | Loaders call Dispatch at night when they cannot reach EWP/Saco supervisor about a missing load | Dispatch | Meeting with loaders to tell them to use Nextel or wait until the morning and leave a message | Quality of Life | Easy | Cathy | 2007-06-19 | 2007-07-13 |  | Meet with Chris and Matt
13 | Sort worksheets by state | Dispatch | Print by State | Medium | Medium | Ed | 2007-06-19 | 2007-07-20
14 | Kelly checks orders for missing delivery info on Day 3 | Shipping Admin | No need to do this, all orders will have delivery info by this step | High | Medium | See # 7 | 2007-06-19 | 2007-07-20
15 | Create Map Cover Sheet typing in existing info (address, project name, customer) | Dispatch | Have form on-line so Job # fills in automatically and can add general directions Scan in faxed maps to order file | Medium | Medium | Ed | 2007-06-19 | 2007-08-01
16 | Create Booking Sheet | Dispatch | New process that creates this in the system | High | done |  |  | 2007-06-19 | Closed
16a | Copy cover sheet | Dispatch | New process that creates this in the system | High | done |  |  | 2007-06-19 | Closed
17 | Sort by state (afternoon) | Dispatch | Print by State | Medium | Medium | See #13 | 2007-06-19 | 2007-07-20
18 | Wrong address cannot deliver | Driver | Sales rep asks for Contractor Cell Phone #, this is the number that Kelly and everyone else calls | High | Easy | See #7 | 2007-06-19 | 2007-07-20
19 | Hold POD until order is complete | Shipping Admin | Don't hold POD, let shipped items go on and be invoiced what we shipped, even if it isn't the entire order | High | Easy | Cathy/ Tim / Jim | 2007-06-19 | 2007-06-29 |  | Need to check what happens with Home Depot, Lowes, Wicks, ???
19a | Hold POD until order is complete | Shipping Admin | Create a daily "not-shipped" (backorder) report Continue notifying sales for rush replacement | High | Easy | Ed | 2007-06-19 | 2007-07-20
20 | Stamp date on PODs | Shipping Admin | Stop Doing | Low | Easy | Cathy | 2007-06-19 | 2007-06-20
22 | Print Daily $ Delivery Report | Shipping Admin | Stop Doing | Medium | Easy | Cathy | 2007-06-19 | 2007-06-20
23 | Calculate Estimated vs. Actual Miles | Shipping Admin | Easier method for getting estimated mileage, use GPS for actual | High | Medium | Cathy/ Ed | 2007-06-19 | 2007-07-30
24 | Stage by State then move to transfer to Saco or stage by load | Loaders | Automate truss linkage to EWP and call a transfer (Start Doing This) | High | Easy | Ed/Matt | 2007-06-19 | 2007-06-29
25 | Put finished trusses in central location | Factory | Put right in "load" staging area, After yard is 5S | High | Easy | Chris | 2007-06-19 | 2007-07-20
26 | List orders on Yard Map | Loaders | Put right in "load" staging area, After yard is 5S Produce abridged version of loaders report by: Load #, Trailer, Sales Order #, Show Status | High | Easy | Ed/Chris | 2007-06-19 | 2007-07-20
31 | Wall Panel production loads wall panels on trucks | Wall Panel Prod'n | Need separate loader schedule Have loaders start to load | High | Medium | Ed/Matt | 2007-06-19
32 | Printing two different versions of the same loader-report | Dispatch | Use only one version | Low | Easy | Cathy | 2007-05-30 | 2007-05-18 | Closed
33 | Make hand-written Biddeford load map | Loaders | Produce abridged version of loaders report by: Load #, Trailer, Sales Order #, Show Status | High | Easy | Ed/Matt | 2007-06-19 | 2007-07-20
35 | Put Saco transfers in one location | Loaders | Automate truss linkage to EWP and call a transfer (Start Doing This) | High | Easy | See # 24 | 2007-06-19 | 2007-06-29
39 | Fill out RMA form | Sales Reps | Take info off RMA paper-form (date, customer name, return #, address, contact, phone, customer PO#, job name) | High | Easy | Tim | 2007-06-19 | 2007-07-13
40 | Obtain customer code and put on RMA | DC Admin | Sales Reps print VB quote and attach to new streamlined RMA paper form, to give to Debbie | Low | Easy | Tim | 2007-06-19 | 2007-06-25
41 | Not sending RMA packet to the customer |  | Auto-fax packet with acknowledgement | Medium | Medium | Ed | 2007-06-19 | 2007-07-30
42 | Emailing RMA to Sheila, Andrew, Kenny | DC Admin | Automate as part of faxing to customer | Low | Medium | See #41 | 2007-06-19 | 2007-07-30
43 | Create return material ID Tag | Sales Admin | Automate the creation of this tag | Low | Medium | See #41 | 2007-06-19 | 2007-07-30
44 | Print out Non-Legal Driver Packet documents | Designers | Eliminate all non-legal required documents from the driver packet At least for all customers that never requested this | Medium | Difficult | Tim | 2007-06-19 | 2007-07-20
46 | Make copy of drivers RMA and file | Dispatch | Stop Doing | Medium | Easy | Cathy | 2007-06-19 | 2007-06-20
47 | Use cover sheet and booking sheet to enter Truck recap info Remove non delivery orders and split ships from total delivery $ Enter total delivered sales $ to truck recap Print truck recap Enter daily $ shipped | Shipping Admin | Stop Doing | Medium | Easy | Cathy | 2007-06-19 | 2007-06-20
48
49
50

## Quantify Savings
Issue | Solution | Role | Date Complete | # of People | Freq. Per Year | Duration | Total Time Saved
Sales Rep fills out change order form (filling in all header info) | Sales Rep changes the order in the system (no paper) | Sales Reps | 2007-08-01 |  |  | 0 | 0
Sales Admin Fills out Change-Order Form on-line from paper form (filled out by Sales Rep) | Sales Rep change the order in the system | Sales Admin | 2007-08-01 | 1 | 3250 | 2 | 108.3333
Sales Admin checks for missing delivery info (on order, check folders, call customer) | Enter order, and Sales Rep gets delivery info every time Sales Rep asks for and calls the contractor Field in system for Contractor Phone # Policy for leaving delivery info on our vmail (job #, extension) | Sales Admin | 2007-07-20 | 1 | 750 | 10 | 125
Kelly and Helen meet to review mising delivery info | No need for meeting if Helen is not checking for missing delivery info by calling customers | Shipping Admin | 2007-07-20 | 1 | 250 | 5 | 20.8333
Kelly and Helen meet to review mising delivery info | No need for meeting if Helen is not checking for missing delivery info by calling customers | Sales Admin | 2007-07-20 | 1 | 250 | 5 | 20.8333
Helen finds out that customer needs to cancel/delay/expedite order | No need to do this if Helen is not checking for missing delivery info | Sales Admin | 2007-07-20 | 1 | 0 | 0 | 0
Kelly checks orders for missing delivery info | No need to do this, all orders will have delivery info by this step | Shipping Admin | 2007-07-20 | 1 | 1000 | 15 | 250
Kelly calls for date confirmation | Stop Doing | Shipping Admin | 2007-07-20 |  |  |  | 0
Kelly creates change order form to change delivery date and sends it to Sales Admin to enter | Shipping admin changes the order in the system System must email sales rep all changes to their orders | Shipping Admin | 2007-07-01 | 1 | 1250 | 1 | 20.8333
Print 2 copies of worksheets (1 to keep in order and 1 to sort by state) so Rod can bring a packe thome | Create a report in job # sequence to reference with worksheet details | Dispatch | 2007-07-13 | 1 | 1000 | 1 | 16.6667
Sort worksheets by state | Print by State | Dispatch | 2007-07-20 | 1 | 500 | 2 | 16.6667
Kelly checks orders for missing delivery info on Day 3 | No need to do this, all orders will have delivery info by this step | Shipping Admin | 2007-07-20 | 1 | 750 | 15 | 187.5
Create Map Cover Sheet typing in existing info (address, project name, customer) | Have form on-line so Job # fills in automatically and can add general directions Scan in faxed maps to order file | Dispatch | 2007-08-01 | 1 | 1750 | 3 | 87.5
Create Booking Sheet | New process that creates this in the system | Dispatch | 2007-06-19 | 1 | 5000 | 1 | 83.3333
Copy cover sheet | New process that creates this in the system | Dispatch | 2007-06-19 | 1 | 250 | 1 | 4.1667
Wrong address cannot deliver | Sales rep asks for Contractor Cell Phone #, this is the number that Kelly and everyone else calls | Driver | 2007-07-20 | 1 | 375 | 90 | 562.5
Hold POD until order is complete | Don't hold POD, let shipped items go on and be invoiced what we shipped, even if it isn't the entire order | Shipping Admin | 2007-06-29 | 1 | 375 | 5 | 31.25
Stamp date on PODs | Stop Doing | Shipping Admin | 2007-06-20 | 1 | 250 | 5 | 20.8333
Print Daily $ Delivery Report | Stop Doing | Shipping Admin | 2007-06-20 | 1 | 250 | 1 | 4.1667
Calculate Estimated vs. Actual Miles | Easier method for getting estimated mileage, use GPS for actual | Shipping Admin | 2007-07-30 | 1 | 250 | 60 | 250
Stage by State then move to transfer to Saco or stage by load | Automate truss linkage to EWP and call a transfer (Start Doing This) | Loaders | 2007-06-29 | 1 | 5625 | 10 | 937.5
Put finished trusses in central location | Put right in "load" staging area, After yard is 5S | Factory | 2007-07-20 | 1 | 250 | 240 | 1000
List orders on Yard Map | Put right in "load" staging area, After yard is 5S Produce abridged version of loaders report by: Load #, Trailer, Sales Order #, Show Status | Loaders | 2007-07-20 | 1 | 250 | 10 | 41.6667
Make hand-written Biddeford load map | Produce abridged version of loaders report by: Load #, Trailer, Sales Order #, Show Status | Loaders | 2007-07-20 | 1 | 250 | 10 | 41.6667
Fill out RMA form | Take info off RMA paper-form (date, customer name, return #, address, contact, phone, customer PO#, job name) | Sales Reps | 2007-07-13 | 1 | 1250 | 1 | 20.8333
Obtain customer code and put on RMA | Sales Reps print VB quote and attach to new streamlined RMA paper form, to give to Debbie | DC Admin | 2007-06-25 | 1 | 1250 | 1 | 20.8333
Emailing RMA to Sheila, Andrew, Kenny | Automate as part of faxing to customer | DC Admin | 2007-07-30 | 1 | 1250 | 0.5 | 10.4167
Create return material ID Tag | Automate the creation of this tag | Sales Admin | 2007-07-30 | 1 | 1250 | 1.5 | 31.25
Print out Non-Legal Driver Packet documents | Eliminate all non-legal required documents from the driver packet At least for all customers that never requested this | Designers | 2007-07-20 | 1 | 3750 | 8 | 500
Make copy of drivers RMA and file | Stop Doing | Dispatch | 2007-06-20 | 1 | 1000 | 1 | 16.6667
Use cover sheet and booking sheet to enter Truck recap info Remove non delivery orders and split ships from total delivery $ Enter total delivered sales $ to truck recap Print truck recap Enter daily $ shipped | Stop Doing | Shipping Admin | 2007-06-20 | 1 | 250 | 20 | 83.3333
Note on F17: Mitch Millstein: 50% improvement

## Savings Summary
Sum of Total Time Saved
Role | Total
Designers | 500
Dispatch | 225
Driver | 562.5
Loaders | 1020.8333
Sales Admin | 285.4167
Sales Reps | 20.8333
Shipping Admin | 868.75
Factory | 1000
DC Admin | 31.25
Grand Total | 4514.5833

## Not Implemented Now
# | Issue | Role | Idea/Solution | Benefit (High/Low) | Imp. (Easy/Difficult) | Owner | Start Date | Target Date | Closed? | STATUS
1 | Admin enters sales info from paper form given to them by Sales | Sales Admin | Sales Reps enter their own info for EWP Orders | Medium | Difficult
2 | Sales enters Truss info into system from paper form | Sales Rep | Sales Reps enter the info real-time | Low | Difficult
6 | Note back order while cutting - notify Dave (already been entered and batched) | Purchasing | Accurate Inventory | Not in scope
12b | Loaders call Dispatch at night | Dispatch | Move a person to an Evening/Night Dispatcher | Medium | Difficult
34 | Find cut orders in Biddeford yard | Loaders | No solution due to last minute changes in load plans | High | Impossible
36 | Arranging EWP Loads | Loaders | No solution due to last minute changes in load plans | High | Impossible
37 | Verify latest Loader Report to previous | Loaders | Show what is different from last print | Medium | Impossible
38 | Quality check product on the truck | Loaders | Stop Doing | High | Impossible
29 | Shipping looks at finished bundles to determine how to ship | Dispatch | Wall panel team desiging procedure and process to automate | High | Difficult
30 | Give Load plan to Wall Panel Production to Load | Dispatch | Wall panel team desiging procedure and process to automate | High | Difficult
21 | Put POD in numerical order for looking up later to deal with problems | Sales Admin | Stop storing the POD with Alternate job-site proof of delivery Scan POD and link to job file | Medium | Medium